## Instructions
1. INTRODUCTION
This country reporting framework has been developed following the structure of the FCPF Monitoring and Evaluation Framework. The semi-annual country reporting should provide the FMT with indications of REDD+ countries’ progress towards the achievement of their readiness activities and the implementation of their ER programs overtime, in a way that data are easily consolidated and provide indications on the level of achievement of the FCPF output, outcome and impact indicators as defined in the FCPF M&E Framework.
Submitted country reports should draw upon the country M&E system for REDD + (component 6 of R-PP) and should be prepared in consultation with members of REDD task force or equivalent body as well your Delivery Partner (IDB, World Bank or UNDP). Inputs from stakeholders including IPs and CSOs should be integrated into national reporting, and divergent views indicative of lack of consensus on specific issues should be recorded in the country report.
It is expected that the annual progress country reporting will be submitted to the FMT by August 15th each year. A self-assessment of progress will be conducted as part of this country reporting. An update of this country reporting will also be submitted by March 15th each year.
2. INSTRUCTIONS
Color Coding of Survey Fields
Dark blue fields as headings that match your R-PP and the M&E Framework
Follow the Instructions in the White fields
Fill in fields with the blue color to the best of your ability
Note: | Information is to be provided cumulatively. If the information requested is not available or not relevant at the time of the reporting, simply put “does not apply – n/a” in the appropriate field.
3. HELP
For help or questions, do not hesitate to email Erin Conner, Neeta Hooda or Kate Cecys.
| Kate Cecys: | Kcecys@worldbank.org
| Erin Conner: | Econner@worldbank.org
| Neeta Hooda: | Nhooda@worldbank.org
4. PRINT COMPLETE WORKBOOK
To print the entire Survey Excel Workbook go to:
File-->Print-->Settings and select "Print Entire Workbook"
Start

## Partcipant Detail
Please Provide Contact Information:
Partcipant Details:
Contact Country:
Contact Name 1:
Title 2:
Contact Name 2:
Title 2:
Contact Email:
Alternate Email:
Contace Telephone:
Alternate Telephone:
Submission Date:
Next Page
Previous Page

## Sheet 1- Sections 1-2
1. GENERAL INTRODUCTION
Q1 | Introduction to the report, its main purpose and sections. Short description of FCPF support in country.
A1 | Limit to one page of text
2. SUMMARY OF REPORT
Q2 | Summary of progress, key achievements with a focus on higher level results and important issues/problems that arose during the reporting period. Highlights of next steps in following period -- key bullets only
Progress:
A2
Q3 | Key Achievements with focus on higher level results:
A3 | Limit to half page of text
Q4 | Important issues /problems that arose during the reporting period:
A4 | Limit to half page of text
Q5 | Highlights of next steps in the following period:
A5 | Limit to half page of text
Next Page
Previous Page

## Sheet 2 - Sections 3-3.2.1
3. MAIN ACHIEVEMENTS AND RESULTS DURING THE PERIOD
The section below should provide qualitative and quantitative data on the progress towards expected results along the following subsections. Information is to be provided cumulatively. If the information requested is not available or not relevant at the time of the reporting, mention “does not apply – n/a”.
3.1 PROGRESS AT THE IMPACT LEVEL (if any data available)
Q3.1 | Please provide here any quantitative and qualitative information, if available on the following criteria/indicators.
A3.1 | free text
Number of tons of CO2 emissions from deforestation and forest degradation reduced in the country during the reporting period as compared to the measured REL/RL, if any :
Q3.1.1 | National Forest Reference Emission Level (REL)/Reference Level (RL) defined:
A3.1.1
Q3.1.2 | Number of tons reduced during the reporting period as compared to REL/RL:
A3.1.2
Amount of non-FCPF investments received under R-PP process:
Q3.1.3 | Source: |  | <Select> | Amount Provided:
A3.1.3.1 | free text | A3.1.4.1 | Currency
A3.1.3.2 | free text | A3.1.4.2 | Currency
A3.1.3.3 | free text | A3.1.4.3 | Currency
Amount of non-FCPF investments received for implementation of ER Programs (e.g. FIP, bilateral donors, private sector), if relevant:
| Source: |  | <Select> | Amount Provided:
Currency
Currency
Currency
Currency
Currency
Level of multi-stakeholder participation and engagement in decision making processes related to emission reductions and forest resource management:
Please describe the process of engagement and consultation implemented, including describing the level of participation and engagement for the following stakeholder categories: Government Agencies, Indigenous Peoples, Other forest-dependent peoples, Women, Youth, Civil Society Organizations, Private Entities, Donors, and Others
free text
Nb. and type of policy reforms underway or completed complying to REDD+ standards, if any (FCPF M&E Framework Indicator I.3.B.):
Number of policy reforms during the reporting period that are: <Select from dropdown list>
| Underway: |  | #
#
#
#
| Completed: |  | #
#
#
Please describe these policy reforms:
limit to 1 page
3.2 PROGRESS AT THE OUTPUT and OUTCOME LEVEL (if any data available)
3.2.1. REDD Readiness Progress
OUTCOME LEVEL
As a synthesis of the following output level assessments, please briefly describe here the progress made during the reporting period in developing the country Readiness Package (FCPF M&E Framework Indicator 1.A.):
Briefly describe progress made during the reporting period in developing the country Readiness Package:
free text limit to .5 page
OUTPUT LEVEL
Please indicate which of your country R-PP components and sub-components have received support from FCPF through the Readiness Preparation Grant (>3.4 million USD)
| Component |  |  | Support from FCPF (Yes/No)
Component 1. Readiness Organization and Consultation
1a. National REDD+ Management Arrangements
1b. Consultation, Participation, and Outreach
Component 2. REDD+ Strategy Preparation
2a. Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance
2b. REDD+ Strategy Options
2c. Implementation Framework
2d. Social and Environmental Impacts
Component 3. REL/RL
3. Reference Emissions Level/Reference Levels
Component 4. Monitoring Systems for Forests and Safeguards
4a. National Forest Monitoring System
4b. Information System for Multiple Benefits, Other Impacts, Governance, and Safeguards
Level of implementation of R-PP as a whole:
| Please describe the current R-PP implementation stage: | % Completed:
Level of achievement of planned milestones according to approved FCPF-financed Readiness Fund Grant (>3.8 million USD) (FCPF M&E Framework 1.3b):
| Planned Milestones: | Level of Achievement: |  | Tracking:
1
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Group Box 124
Next Page
Previous Page

## Sheet 3 - Disbursements 3.2.2
3.2.1. CONTINUED Disbursement rate of FCPF-financed Readiness Fund Grant (>3.4 million USD), in %
RF Grant - disbursement rate compared to planned disbursement rate
Disbursement rate of FCPF-financed Readiness Fund Grant (>3.4 million USD), in percentage:
| Select Actual Disbursement Rate | Tracking | 3
RF Grant - actual disbursement rate compared to planned disbursement rate | 10% | 3
Disbursement rate of Total R-PP Budget in percentage:
| Select Actual Disbursement Rate | Tracking
R-PP Budget - disbursement rate v planned disbursement rate | 70% | 2
Next Page
Previous Page
Up to 10% variance with plans
Between 10 and 25% variance
Between 25 and 40% variance
More than 40% variance
Not Applicable
Up to 10% variance with plans
Between 10 and 25% variance
Between 25 and 40% variance
More than 40% variance
Not Applicable

## Sheet 4 3.2.1 cont'd
3.2.1. REDD Progress Levels - Continued
Countries are expected to provide data on the overall level of achievement of planned milestones as defined in their Readiness Preparation Grant Agreement, and, if applicable, on their Supplementary Grant Agreement (additional grant of up to $5 million). Under their Preparation Readiness Grant Agreement (>3.4 million USD), Countries should provide data on (i) the support to the Coordination of the REDD+ Readiness Process and Multi-Stakeholder Consultations; (ii) the contribution to the Design of a National REDD+ Strategy; and (iii) the preparation of a National Reference Scenario for REDD+ The level of achievement of planned milestones according to the Readiness grant will be summarized through progress scores related to the synthesis of an overall achievement. This is qualitatively expressed with a four-color ‘traffic light’ scale and then explained. In case the assessment is not applicable, “Non Applicable” can be selected. The level of achievement of planned milestones per R-PP component should be self-assessed and reported, as well as summarized through progress scores related to the synthesis of this overall achievement, qualitatively expressed on a four-color ‘traffic light’ scale and then briefly explained. In case the assessment is not applicable, a fifth color scale ‘Non Applicable’ can be selected. This ‘traffic light’ scale is based on the system contained in the R-Package Assessment Framework, The R-Package assessment criteria are included to assist countries identify, plan and track their readiness preparations progress with the core aspects and desired outcomes of readiness preparation activities as contained in R-Package Assessment Framework.
Sub-Component 1a | Overall Progress |  | Progress Against Annual Targets |  | Tracking* | 4
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target
1a - National REDD+ Management Arrangements Purpose: setting-up national readiness management arrangements to manage and coordinate the REDD-plus readiness activities whilst mainstreaming REDD-plus into broader strategies Assessment Criteria: (i) accountability and transparency; (ii) operating mandate and budget; (iiI) multi-sector coordination mechanisms and cross-sector collaboration; (iv) technical supervision capacity; (v) funds management capacity; (vi) feedback and grievance redress mechanism |  |  |  |  | 4
4
Sub-Component 1b | Overall Progress |  | Progress Against Annual Targets |  | Tracking
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 1
1b – Consultation, Participation, and Outreach Purpose: broad consultation with and participation of key stakeholders for future REDD+ programs, to ensure participation of different social groups, transparency and accountability of decision-making Assessment Criteria: (i) participation and engagement of key stakeholders; (ii) consultation processes; (iii) information sharing and accessibility of information; (iv) implementation and public disclosure of consultation outcomes |  |  |  |  | 1
Sub-Component 2a | Overall Progress |  | Progress Against Annual Targets |  | Tracking
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target
2a: Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance Purpose: identify key drivers of deforestation and/or forest degradation, as well as activities concerning conservation, sustainable forest management, and enhancement of forest carbon stocks Assessment Criteria: (i) assessment and analysis; (ii) prioritization of direct and indirect drivers/barriers to forest enhancement; (iii) links between drivers/barriers and REDD+ activities; (iv) actions plans to address natural resource rights, land tenure, governance; (v) implications for forest law and policy |  |  |  |  | 4 | 4
4
Sub-Component 2b | Overall Progress |  | Progress Against Annual Targets |  | Tracking
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
2b: REDD+ Strategy Options Purpose: Develop a set of policies and programs for addressing the drivers of deforestation and/or forest degradation Assessment Criteria: (i) selection and prioritization of REDD+ strategy options; (ii) feasibility assessment; (iii) implications for strategy options on existing sectoral policies |  |  |  |  | 4 | 0
0
0
0
0
0
0
0
Sub-Component 2c | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 5
2c: Implementation Framework Purpose: Set out credible and transparent institutional, economic, legal and governance arrangements necessary to implement REDD+ strategy options Assessment Criteria: (i) adoption and implementation of legislation/regulations; (ii) guidelines for implementation; (iii) benefit sharing mechanism; (iv) national REDD+ registry and system monitoring REDD+ activities |  |  |  |  | 5 | 0
0
0
0
0
0
0
0
Sub-Component 2d | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
2d: Social and Environmental Impacts Purpose: Ensure compliance with the Common Approach and prepare a country specific Environmental and Social Management Framework (ESMF) Assessment Criteria: (i)) analysis of social and environmental safeguard issues; (ii) REDD+ strategy design with respect to impacts; (iii) Environmental and Social Management Framework |  |  |  |  | 4 | 0
0
0
0
0
0
0
0
0
Component 3 | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 3
R-PP Component 3 - Reference Emissions Level/Reference Levels Purpose: Development of the general approach to establish a REL/RL Assessment Criteria: (i) demonstration of methodology; (ii) use of historical data, and adjusted for national circumstances; (iii) technical feasibility of the methodological approach, and consistency with UNFCCC/IPCC guidance and guidelines |  |  |  |  | 3 | 0
0
0
0
0
0
0
Sub-Component 4a | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 5
4a: National Forest Monitoring System Purpose: Design and develop an operational forest monitoring system and describe the approach to enhance the system over time Assessment Criteria: (i) documentation of monitoring approach; (ii) demonstration of early implementation; (iii) institutional arrangements and capacities- Forests |  |  |  |  | 5 | 0
0
0
0
0
0
0
#REF!
0
Sub-Component 4b | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
4b: Information System for Multiple Benefits, Other Impacts, Governance, and Safeguards Purpose: Specify the non-carbon aspects prioritized for monitoring by the country Assessment Criteria: (i) identification of relevant non-carbon aspects, and social and environmental issues; (ii) monitoring, reporting and information sharing; (iii) Institutional arrangements and capacities – Safeguards |  |  |  |  | 4 | 0
0
0
*This ‘traffic light’ scale is based on the system contained in the R-Package Assessment Framework, The R-Package assessment criteria are included to assist countries identify, plan and track their readiness preparations progress with the core aspects and desired outcomes of readiness preparation activities as contained in R-Package Assessment Framework.
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Next Page
Previous Page
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable

## Sheet 5 - 3.2.3 - 3.2.4
3.2.3. Engagement of stakeholders to sustain or enhance livelihoods of local communities and to conserve biodiversity within the approach to REDD+
OUTCOME LEVEL
As a synthesis of the following output level assessments, please describe indicators related to biodiversity conservation and forest community livelihood development included in the ER Program if relevant (FCPF M&E Framework indicator 3.A.):
Amount provided: |  | Currency
Please describe how these funds target biodiversity and forest community livelihood development: |  | Free Text
Please provide relevant examples on the inherent social and biodiversity benefits of REDD+, if relevant (FCPF M&E Framework Indicator 3.B.):
1
Examples of inherent social and biodiversity benefits of REDD+:
Free text
OUTPUT LEVEL
Number of examples of actions where Ips, CSOs, and local communities participate actively, if relevant (FCPF M&E Framework 3.2.a.):
#: | Please describe these actions on enhanced livelihoods and BD conservation, and restoration where Ips, CSO, and local communities participate actively:
Number of IPs, REDD Country CSO representatives (men/women) having been successfully trained by FCPF training programs (FCPF M&E Framework 3.1.b.):
Please list the training(s) conducted: | Duration (#of days) | # of participants |  | Rating
|  | # of men | # of women
Free text |  |  |  | 2
Frequency of meetings of stakeholder engagement platforms (FCPF M&E Framework 3.2.a.):
Frequency: |  |  | Rating
2
Does your country R-Package (within the national REDD+ strategies and the monitoring systems) and/or ER Program include activities aiming at maintaining or enhancing livelihoods of local communities (FCPF M&E Framework 3.2.b.):
Yes/No: | Please describe these activities aiming at maintaining or enhancing livelihoods of local communities:
Yes no | Free text
Does your country R-Package (within the national REDD+ strategies and the monitoring systems) and/or ER Program include activities aiming at conserving biodiversity (FCPF M&E Framework 3.2.c.)?
Yes/No: | Please describe these activities aiming at conserving biodiversity:
Yes no | Free text
Does your country R-Package and/or ER Program include SESA, an operational Grievance Mechanism, and an ESMF that captures SESA results (FCPF M&E Framework 3.2.d.)?
Yes/No: | Please describe these activities aiming at conserving biodiversity:
Yes no | Free text
3.2.4 Knowledge Sharing
Has your country developed and published REDD+ knowledge products with FCPF support?
Yes/No: | If yes, please provide a list of the published REDD+ knowledge products if any, during the reporting period:
Yes/No | 1
2
3
4
…
How many people have been reached by these knowledge products, if any?
Overall number by product: | Please provide a list of the published REDD+ knowledge products if any, during the reporting period:
Knowledge Product 1:
# Total People Reached
# of Men
# of Women
Knowledge Product 2:
# Total People Reached
# of Men
# of Women
Knowledge Product 3:
# Total People Reached
# of Men
# of Women
Knowledge Product 4:
# Total People Reached
# of Men
# of Women
Have some experts of your country participated in any South-South learning activities? If yes, how many?
Yes/No | List the South-South Exchanges: |  | # Men | # Women
Yes/No
Yes/No
Yes/No
Yes/No
Next Page
Previous Page
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable

## Sheet 6 - Disbursements 3.2.2
3.2.2. Key Elements of performance based payment systems for emission reductions generated from REDD+ activities
OUTCOME LEVEL
As a synthesis of the following output level assessments, please briefly specify:
Are carbon accounting, programmatic elements and pricing operating as planned in your pilot, if relevant? |  |  | 15
Tracking
Free text |  |  |  | 1
Is the benefit sharing scheme being implemented according to plans within your pilot, if relevant?
Tracking
Free text |  |  |  | 1
Percentage and/or amount of monetary benefits shared with beneficiaries in approved pilot, if relevant?
Tracking
Free text |  |  |  | 3
OUTPUT LEVEL
As a synthesis of the following output level assessments, please briefly specify:
Has your country submitted early ideas or ER-Program to the Carbon Fund and or others?
Yes/No | Please briefly describe the content of these early ideas or ER-Program:
Yes/No | Free Text
Has your country signed an ERPA?
Has your country submitted early ideas or ER-Program to the Carbon Fund and or others?
Yes/No | Please briefly describe the content of this ERPA:
Yes/No | Free Text
Amount and date of disbursements for ER Program according to plans, if relevant:
Date format: | mm/dd/yyyyy |  | <Select>
Date: |  | Amount provided: | Currency
Date: |  | Amount provided: | Currency
Date: |  | Amount provided: | Currency
Next Page
Previous Page
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable

## Sheet 7 Sections 4 -5 I, C,R
4. Issues Challenges and Risks
This section should present any problems, difficulties or constraints faced by the country in making progress towards the intended REDD+ results (outputs, outcomes and possible impacts), the main causes and their expected effect on the work plan. Actions that have been taken to overcome or manage these constraints/flaws/problems identified should be stated. Each problem/constraint should be stated as a separate point, along with associated proposed changes in work planning for the next six month/year to address it, as relevant.
Issue, Challenge, Risk | Actions to overcome, Adjustments to plan
5. Main Lessons Learned
This section should be used to provide information on important lessons learnt since the beginning of the readiness process. As this is a semi-annual report, it is expected that this section will be fairly substantial, making reference to different lessons learning documents, and/or events developed and dealing with issues of particular interest with respect to readiness of carbon funding under REDD+.
Free text
Complete
Previous Page

## REF (hidden)
a
5 | Significant progress |  |  | Actual Disbursement Rate |  | Issue_Challenge_Risk
4 | Progressing well, further development required |  |  | 10% |  | Operational |  | Code | Combo | Country
3 | Further development required |  |  | 40% |  | Institutional |  | £ | £ - Pound | Pound
2 | Not yet demonstrating progress |  |  | 70% |  | Financial |  | € | € - Euro | Euro
1 | Non Applicable |  |  | 85% |  | Other |  | $ | $ - USD | USD
[8 empty] | ¥ | ¥ - Yen | Yen
[8 empty] | AED | AED - United Arab Emirates Dirham | United Arab Emirates Dirham
|  | Page | Characters |  |  |  |  | AFN | AFN - Afghanistan Afghani | Afghanistan Afghani
| YesNo | page | 32000 |  |  |  |  | ALL | ALL - Albania Lek | Albania Lek
| Yes | halfpage | 1600 |  |  |  |  | AMD | AMD - Armenia Dram | Armenia Dram
| No | [6 empty] | ANG | ANG - Netherlands Antilles Guilder | Netherlands Antilles Guilder
[8 empty] | AOA | AOA - Angola Kwanza | Angola Kwanza
[8 empty] | ARS | ARS - Argentina Peso | Argentina Peso
[8 empty] | AUD | AUD - Australia Dollar | Australia Dollar
[8 empty] | AWG | AWG - Aruba Guilder | Aruba Guilder
[8 empty] | AZN | AZN - Azerbaijan New Manat | Azerbaijan New Manat
[8 empty] | BAM | BAM - Bosnia and Herzegovina Convertible Marka | Bosnia and Herzegovina Convertible Marka
[8 empty] | BBD | BBD - Barbados Dollar | Barbados Dollar
[8 empty] | BDT | BDT - Bangladesh Taka | Bangladesh Taka
[8 empty] | BGN | BGN - Bulgaria Lev | Bulgaria Lev
[8 empty] | BHD | BHD - Bahrain Dinar | Bahrain Dinar
[8 empty] | BIF | BIF - Burundi Franc | Burundi Franc
[8 empty] | BMD | BMD - Bermuda Dollar | Bermuda Dollar
[8 empty] | BND | BND - Brunei Darussalam Dollar | Brunei Darussalam Dollar
[8 empty] | BOB | BOB - Bolivia Boliviano | Bolivia Boliviano
[8 empty] | BRL | BRL - Brazil Real | Brazil Real
[8 empty] | BSD | BSD - Bahamas Dollar | Bahamas Dollar
[8 empty] | BTN | BTN - Bhutan Ngultrum | Bhutan Ngultrum
[8 empty] | BWP | BWP - Botswana Pula | Botswana Pula
[8 empty] | BYR | BYR - Belarus Ruble | Belarus Ruble
[8 empty] | BZD | BZD - Belize Dollar | Belize Dollar
[8 empty] | CAD | CAD - Canada Dollar | Canada Dollar
[8 empty] | CDF | CDF - Congo/Kinshasa Franc | Congo/Kinshasa Franc
[8 empty] | CHF | CHF - Switzerland Franc | Switzerland Franc
[8 empty] | CLP | CLP - Chile Peso | Chile Peso
[8 empty] | CNY | CNY - China Yuan Renminbi | China Yuan Renminbi
[8 empty] | COP | COP - Colombia Peso | Colombia Peso
[8 empty] | CRC | CRC - Costa Rica Colon | Costa Rica Colon
[8 empty] | CUC | CUC - Cuba Convertible Peso | Cuba Convertible Peso
[8 empty] | CUP | CUP - Cuba Peso | Cuba Peso
[8 empty] | CVE | CVE - Cape Verde Escudo | Cape Verde Escudo
[8 empty] | CZK | CZK - Czech Republic Koruna | Czech Republic Koruna
[8 empty] | DJF | DJF - Djibouti Franc | Djibouti Franc
|  |  | list of countries: |  | Argentina |  |  | DKK | DKK - Denmark Krone | Denmark Krone
[5 empty] | Bolivia |  |  | DOP | DOP - Dominican Republic Peso | Dominican Republic Peso
[5 empty] | Cambodia |  |  | DZD | DZD - Algeria Dinar | Algeria Dinar
[5 empty] | Cameroon |  |  | EGP | EGP - Egypt Pound | Egypt Pound
[5 empty] | CAR |  |  | ERN | ERN - Eritrea Nakfa | Eritrea Nakfa
[5 empty] | Chile |  |  | ETB | ETB - Ethiopia Birr | Ethiopia Birr
[5 empty] | Colombia |  |  | EUR | EUR - Euro Member Countries | Euro Member Countries
[5 empty] | Costa Rica |  |  | FJD | FJD - Fiji Dollar | Fiji Dollar
[5 empty] | DR Congo |  |  | FKP | FKP - Falkland Islands (Malvinas) Pound | Falkland Islands (Malvinas) Pound
[5 empty] | El Salvador |  |  | GBP | GBP - United Kingdom Pound | United Kingdom Pound
[5 empty] | Ethiopia |  |  | GEL | GEL - Georgia Lari | Georgia Lari
[5 empty] | Gabon |  |  | GGP | GGP - Guernsey Pound | Guernsey Pound
[5 empty] | Ghana |  |  | GHS | GHS - Ghana Cedi | Ghana Cedi
[5 empty] | Guatemala |  |  | GIP | GIP - Gibraltar Pound | Gibraltar Pound
[5 empty] | Guyana |  |  | GMD | GMD - Gambia Dalasi | Gambia Dalasi
[5 empty] | Honduras |  |  | GNF | GNF - Guinea Franc | Guinea Franc
[5 empty] | Indonesia |  |  | GTQ | GTQ - Guatemala Quetzal | Guatemala Quetzal
[5 empty] | Kenya |  |  | GYD | GYD - Guyana Dollar | Guyana Dollar
[5 empty] | Lao PDR |  |  | HKD | HKD - Hong Kong Dollar | Hong Kong Dollar
[5 empty] | Liberia |  |  | HNL | HNL - Honduras Lempira | Honduras Lempira
[5 empty] | Madagascar |  |  | HRK | HRK - Croatia Kuna | Croatia Kuna
[5 empty] | Mexico |  |  | HTG | HTG - Haiti Gourde | Haiti Gourde
[5 empty] | Mozambique |  |  | HUF | HUF - Hungary Forint | Hungary Forint
[5 empty] | Nepal |  |  | IDR | IDR - Indonesia Rupiah | Indonesia Rupiah
[5 empty] | Nicaragua |  |  | ILS | ILS - Israel Shekel | Israel Shekel
[5 empty] | Panama |  |  | IMP | IMP - Isle of Man Pound | Isle of Man Pound
[5 empty] | PNG |  |  | INR | INR - India Rupee | India Rupee
[5 empty] | Paraguay |  |  | IQD | IQD - Iraq Dinar | Iraq Dinar
[5 empty] | Peru |  |  | IRR | IRR - Iran Rial | Iran Rial
[5 empty] | Republic of Congo |  |  | ISK | ISK - Iceland Krona | Iceland Krona
[5 empty] | Suriname |  |  | JEP | JEP - Jersey Pound | Jersey Pound
[5 empty] | Tanzania* |  |  | JMD | JMD - Jamaica Dollar | Jamaica Dollar
[5 empty] | Thailand |  |  | JOD | JOD - Jordan Dinar | Jordan Dinar
[5 empty] | Uganda |  |  | JPY | JPY - Japan Yen | Japan Yen
[5 empty] | Vanuatu |  |  | KES | KES - Kenya Shilling | Kenya Shilling
[5 empty] | Vietnam |  |  | KGS | KGS - Kyrgyzstan Som | Kyrgyzstan Som
[8 empty] | KHR | KHR - Cambodia Riel | Cambodia Riel
[8 empty] | KMF | KMF - Comoros Franc | Comoros Franc
[8 empty] | KPW | KPW - Korea (North) Won | Korea (North) Won
[8 empty] | KRW | KRW - Korea (South) Won | Korea (South) Won
[8 empty] | KWD | KWD - Kuwait Dinar | Kuwait Dinar
[8 empty] | KYD | KYD - Cayman Islands Dollar | Cayman Islands Dollar
[8 empty] | KZT | KZT - Kazakhstan Tenge | Kazakhstan Tenge
[8 empty] | LAK | LAK - Laos Kip | Laos Kip
[8 empty] | LBP | LBP - Lebanon Pound | Lebanon Pound
[8 empty] | LKR | LKR - Sri Lanka Rupee | Sri Lanka Rupee
[8 empty] | LRD | LRD - Liberia Dollar | Liberia Dollar
[8 empty] | LSL | LSL - Lesotho Loti | Lesotho Loti
[8 empty] | LTL | LTL - Lithuania Litas | Lithuania Litas
[8 empty] | LVL | LVL - Latvia Lat | Latvia Lat
[8 empty] | LYD | LYD - Libya Dinar | Libya Dinar
[8 empty] | MAD | MAD - Morocco Dirham | Morocco Dirham
[8 empty] | MDL | MDL - Moldova Leu | Moldova Leu
[8 empty] | MGA | MGA - Madagascar Ariary | Madagascar Ariary
[8 empty] | MKD | MKD - Macedonia Denar | Macedonia Denar
[8 empty] | MMK | MMK - Myanmar (Burma) Kyat | Myanmar (Burma) Kyat
[8 empty] | MNT | MNT - Mongolia Tughrik | Mongolia Tughrik
[8 empty] | MOP | MOP - Macau Pataca | Macau Pataca
[8 empty] | MRO | MRO - Mauritania Ouguiya | Mauritania Ouguiya
[8 empty] | MUR | MUR - Mauritius Rupee | Mauritius Rupee
[8 empty] | MVR | MVR - Maldives (Maldive Islands) Rufiyaa | Maldives (Maldive Islands) Rufiyaa
[8 empty] | MWK | MWK - Malawi Kwacha | Malawi Kwacha
[8 empty] | MXN | MXN - Mexico Peso | Mexico Peso
[8 empty] | MYR | MYR - Malaysia Ringgit | Malaysia Ringgit
[8 empty] | MZN | MZN - Mozambique Metical | Mozambique Metical
[8 empty] | NAD | NAD - Namibia Dollar | Namibia Dollar
[8 empty] | NGN | NGN - Nigeria Naira | Nigeria Naira
[8 empty] | NIO | NIO - Nicaragua Cordoba | Nicaragua Cordoba
[8 empty] | NOK | NOK - Norway Krone | Norway Krone
[8 empty] | NPR | NPR - Nepal Rupee | Nepal Rupee
[8 empty] | NZD | NZD - New Zealand Dollar | New Zealand Dollar
[8 empty] | OMR | OMR - Oman Rial | Oman Rial
[8 empty] | PAB | PAB - Panama Balboa | Panama Balboa
[8 empty] | PEN | PEN - Peru Nuevo Sol | Peru Nuevo Sol
[8 empty] | PGK | PGK - Papua New Guinea Kina | Papua New Guinea Kina
[8 empty] | PHP | PHP - Philippines Peso | Philippines Peso
[8 empty] | PKR | PKR - Pakistan Rupee | Pakistan Rupee
[8 empty] | PLN | PLN - Poland Zloty | Poland Zloty
[8 empty] | PYG | PYG - Paraguay Guarani | Paraguay Guarani
[8 empty] | QAR | QAR - Qatar Riyal | Qatar Riyal
[8 empty] | RON | RON - Romania New Leu | Romania New Leu
[8 empty] | RSD | RSD - Serbia Dinar | Serbia Dinar
[8 empty] | RUB | RUB - Russia Ruble | Russia Ruble
[8 empty] | RWF | RWF - Rwanda Franc | Rwanda Franc
[8 empty] | SAR | SAR - Saudi Arabia Riyal | Saudi Arabia Riyal
[8 empty] | SBD | SBD - Solomon Islands Dollar | Solomon Islands Dollar
[8 empty] | SCR | SCR - Seychelles Rupee | Seychelles Rupee
[8 empty] | SDG | SDG - Sudan Pound | Sudan Pound
[8 empty] | SEK | SEK - Sweden Krona | Sweden Krona
[8 empty] | SGD | SGD - Singapore Dollar | Singapore Dollar
[8 empty] | SHP | SHP - Saint Helena Pound | Saint Helena Pound
[8 empty] | SLL | SLL - Sierra Leone Leone | Sierra Leone Leone
[8 empty] | SOS | SOS - Somalia Shilling | Somalia Shilling
[8 empty] | SPL* | SPL* - Seborga Luigino | Seborga Luigino
[8 empty] | SRD | SRD - Suriname Dollar | Suriname Dollar
[8 empty] | STD | STD - São Tomé and Príncipe Dobra | São Tomé and Príncipe Dobra
[8 empty] | SVC | SVC - El Salvador Colon | El Salvador Colon
[8 empty] | SYP | SYP - Syria Pound | Syria Pound
[8 empty] | SZL | SZL - Swaziland Lilangeni | Swaziland Lilangeni
[8 empty] | THB | THB - Thailand Baht | Thailand Baht
[8 empty] | TJS | TJS - Tajikistan Somoni | Tajikistan Somoni
[8 empty] | TMT | TMT - Turkmenistan Manat | Turkmenistan Manat
[8 empty] | TND | TND - Tunisia Dinar | Tunisia Dinar
[8 empty] | TOP | TOP - Tonga Pa'anga | Tonga Pa'anga
[8 empty] | TRY | TRY - Turkey Lira | Turkey Lira
[8 empty] | TTD | TTD - Trinidad and Tobago Dollar | Trinidad and Tobago Dollar
[8 empty] | TVD | TVD - Tuvalu Dollar | Tuvalu Dollar
[7 empty] | $ | TWD | TWD - Taiwan New Dollar | Taiwan New Dollar
[8 empty] | TZS | TZS - Tanzania Shilling | Tanzania Shilling
[8 empty] | UAH | UAH - Ukraine Hryvna | Ukraine Hryvna
[8 empty] | UGX | UGX - Uganda Shilling | Uganda Shilling
[8 empty] | USD | USD - United States Dollar | United States Dollar
[8 empty] | UYU | UYU - Uruguay Peso | Uruguay Peso
[8 empty] | UZS | UZS - Uzbekistan Som | Uzbekistan Som
[8 empty] | VEF | VEF - Venezuela Bolivar | Venezuela Bolivar
[8 empty] | VND | VND - Viet Nam Dong | Viet Nam Dong
[8 empty] | VUV | VUV - Vanuatu Vatu | Vanuatu Vatu
[8 empty] | WST | WST - Samoa Tala | Samoa Tala
[8 empty] | XAF | XAF - Communauté Financière Africaine (BEAC) CFA Franc BEAC | Communauté Financière Africaine (BEAC) CFA Franc BEAC
[8 empty] | XCD | XCD - East Caribbean Dollar | East Caribbean Dollar
[8 empty] | XDR | XDR - International Monetary Fund (IMF) Special Drawing Rights | International Monetary Fund (IMF) Special Drawing Rights
[8 empty] | XOF | XOF - Communauté Financière Africaine (BCEAO) Franc | Communauté Financière Africaine (BCEAO) Franc
[8 empty] | XPF | XPF - Comptoirs Français du Pacifique (CFP) Franc | Comptoirs Français du Pacifique (CFP) Franc
[8 empty] | YER | YER - Yemen Rial | Yemen Rial
[8 empty] | ZAR | ZAR - South Africa Rand | South Africa Rand | 1
[8 empty] | ZMW | ZMW - Zambia Kwacha | Zambia Kwacha | 2
[8 empty] | ZWD | ZWD - Zimbabwe Dollar | Zimbabwe Dollar | 3
[9 empty] | Other |  | 4
5
[10 empty] | Land Use | 6
[10 empty] | Tenure | 7
Benefit Sharing
Institutional Reforms
Other
10%
40%
60%
80%

## Database (hidden)
Sheet | Participant ID | Partcipant Details | Contact Country | Contact Name 1 | Title 1 | Contact Name 2 | Title 2 | Contact Email | Alternate Email | Contace Telephone | Alternate Telephone | Submission Date
Partcipant | 11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet1 (hidden)
Q_ID | Section | Questions | A_ID | Answer
Q1 | 1 | Introduction to the report, its main purpose and sections. Short description of FCPF support in country. | A1
Q2 | 2 | Summary of progress, key achievements with a focus on higher level results and important issues/problems that arose during the reporting period. Highlights of next steps in following period -- key bullets only | A2
Q3