## Instructions
1. INTRODUCTION
This country reporting framework has been developed following the structure of the FCPF Monitoring and Evaluation Framework. The semi-annual country reporting should provide the FMT with indications of REDD+ countries’ progress towards the achievement of their readiness activities and the implementation of their ER programs overtime, in a way that data are easily consolidated and provide indications on the level of achievement of the FCPF output, outcome and impact indicators as defined in the FCPF M&E Framework.
Submitted country reports should draw upon the country M&E system for REDD + (component 6 of R-PP) and should be prepared in consultation with members of REDD task force or equivalent body as well your Delivery Partner (IDB, World Bank or UNDP). Inputs from stakeholders including IPs and CSOs should be integrated into national reporting, and divergent views indicative of lack of consensus on specific issues should be recorded in the country report.
It is expected that the annual progress country reporting will be submitted to the FMT by August 15th. A self-assessment of progress will be conducted as part of this country reporting. An update of this country reporting will also be submitted by March 30th each year.
2. INSTRUCTIONS
Color Coding of Survey Fields
Dark blue fields as headings that match your R-PP and the M&E Framework
Follow the Instructions in the White fields
Fill in fields with the blue color to the best of your ability
Note: | Information is to be provided cumulatively. If the information requested is not available or not relevant at the time of the reporting, simply put “does not apply – n/a” in the appropriate field.
3. HELP
For help or questions, do not hesitate to email Erin Conner, Neeta Hooda or Kate Cecys.
| Kate Cecys: | Kcecys@worldbank.org
| Erin Conner: | Econner@worldbank.org
| Neeta Hooda: | Nhooda@worldbank.org
4. PRINT COMPLETE WORKBOOK
To print the entire Survey Excel Workbook go to:
File-->Print-->Settings and select "Print Entire Workbook"
Start

## Partcipant Detail
Please Provide Contact Information:
Partcipant Details:
Contact Country: | Nicaragua
Contact Name 1: | Zenia Salinas
Title 2: | Punto Focal de la Secretaria de FCPF para Nicaragua
Contact Name 2: | Augusto Garcia
Title 2: | Gerente de Poyecto FCPF por BM como socio ejecutor
Contact Email: | agarcia2worldbank.org
Alternate Email:
Contace Telephone:
Alternate Telephone:
Submission Date: | 27 de agosto 2014
Next Page
Previous Page

## Sheet 1- Sections 1-2
1. GENERAL INTRODUCTION
Q1 | Introduction to the report, its main purpose and sections. Short description of FCPF support in country.
A1 | La estrategia Nacional para reducir la Deforestacion y Degradacion ForestalENDE-REDD+ se concibe como el marco politico y estrategico del Estado de Nicaragua, diseñado para integrar las acciones en los niveles nacional, subnacional y local orientadas a revertir las causas que representa dicho fenomeno , considerando los derechos de los pueblos originarios y del pueblo nicaraguense en general a disfrutar de los recursos naturales de forma racional y sostenida. La ENDE-REDD+ funciona sobre la base de la Politica y de la Legislacion Forestal Nacional y de forma ajustada a los requistos de la Declaracion de las Naciones Unidas sobre los derechos de los Pueblos Indigenas(UNDRID) 169 de la OIT, ratificado por el Gobierno de Nicaragua lo que incluye el consentimiento libre, previo e informado de los pueblos indigenas, con respeto a su cultura a su cosmovisión, el uso de su lengua en el proceso de consulta . Se espera que al final del proceso de preparacion se cuente con cuatro productos: Estrategia Nacional de Redd+2) Escenarios de referencia para cubrir adicionalidades 3) Marco estrategico Social y Ambiental SESA, y 4) Un sistema de seguimiento y monitoreo de bosques. Presupuesto estimado: es de US$10 millones Presupuesto disponible a la fecha:3.6 millones de dolares
Summary of progress, key achievements with a focus on higher level results and important issues/problems that arose during the reporting period. Highlights of next steps in following period -- key bullets only
2. SUMMARY OF REPORT
Q2 | Summary of progress, key achievements with a focus on higher level results and important issues/problems that arose during the reporting period. Highlights of next steps in following period -- key bullets only
Progress:
A2 | El proyecto inicia con una Donación equivalente a US$ 200,000.00 para la formulacion de la propuesta lo s resultados fueron:Diálogo intensivo sobre temas técnicos y ámbitos del nivel de participación. Conformación de los 3 niveles de consultivo: Politico, Técnico-Operativo y Diálogo y consulta con la sociedad en general. Documento de Proyecto fue aprobado en forma satisfactorio. Se definieron las líneas estratégicas. Se definieron los cinco (5 )componentes y su presupuesto. La segunda Donacion TF - 099264 administrada por el Banco Mundial US$ 3.6 millones. Project ID: P120657 Financiamiento del la preparacion de Estudios y Actividades por un monto equivalente a 3.600,000 Se ha contratado personal profesional a nivel central y territorial. 12(75%) especialistas de 16 previstos inicialmente Se han cumplido con las condiciones previas: Plan Global, Plan Operativo Anual, Plan de Adquisciones y Manual Operativo (MANOP) Se tiene en proceso de aprobación el Plan de Capacitacion . Se han contratado : Coordinador, Esp En manejo Financiero, Esp. adquisciones, Esp en Monitoreo de Bosques, Esp en Monitoreo de bosques, Esp en Planificacion , seguimiento y evaluacion, Analista contable, Asistente de Coordinacion y Asistente fiduciario, Especialista SESA y los dos Coodinadores Territoriales para la RACCN Y RACCS. Se estan creando las condiciones logisticas para el desarrollo del trabajo: adquisicion de vehiculos y motocicletas, aires acondicionados, y equipo informáticos. Desde el punto de vista técnico se ha logrado instalar los niveles I y II para consulta y dialogo, y se preparan condiciones para conformar los ejes de ejecucion subnacional iniciado con la asignacion de Coordinadores Territoriales seleccionados con participacion de representantes de los pueblos indigenas.
Q3 | se
A3 | Limit to half page of text: Existe una alta expectativa de los pueblos indigenas de la Costa Caribe a que los recursos financieros de esta donación se manejen de manera descentralizada. Además, solicitan que el proyecto llegue a los Gobiernos Territoriales Indígenas (GTI).
Q4 | Important issues /problems that arose during the reporting period:
A4 | Limit to half page of text : En la contratacion de consultores han pedido participacion, ellos quieren a nativos y conocedores de su cultura consultando y diseñando la estrategia, esto se ha facilitado incorparandoles al Comité de evaluación y selección de consultores.- Personal incompleto (especialistas), algunos de los cuales tienen bajo su responsabilidad la elaboración de TdRs para proceso vitales de avance del proyecto. - Caída de procesos de adquisiciones al ser declarados desiertos. - Realización de ajustes al POA y PAC, mismos que serán enviados a la DISUP para aprobación y posterior envió a No Out del Banco Mundial.
Q5 | Highlights of next steps in the following period:
A5 | Una vez conformada la Unidad Coordinadora de proyecto con el equipo completo, estaremos llevando a cabo la administracion de tres contratos de consultoria que nos permitiran identificar los grandes ejes de la estrategia :a)Elaboracion de un Diagnóstico del Marco Legal, Política, Gobernanza y su relación con la ENDE-REDD+ (marco de Referencia e identificacion de vacios y contradicciones en el marco legal vigente) b)Proceso inicial para el establecimiento de los niveles de referencia y linea de base (eje principal de la estrategia ENDE-REDD+) c)Propuesta de Manual de Funciones de los III Niveles de Diálogo y Consulta (Los mecanismo de validacion y elaboracion del plan de implementacion de la ENDE-REDD+).
Next Page
Previous Page

## Sheet 2 - Sections 3-3.2.1
3. MAIN ACHIEVEMENTS AND RESULTS DURING THE PERIOD
The section below should provide qualitative and quantitative data on the progress towards expected results along the following subsections. Information is to be provided cumulatively. If the information requested is not available or not relevant at the time of the reporting, mention “does not apply – n/a”.
3.1 PROGRESS AT THE IMPACT LEVEL (if any data available)
Q3.1 | Please provide here any quantitative and qualitative information, if available on the following criteria/indicators.
A3.1 | Se …..
Number of tons of CO2 emissions from deforestation and forest degradation reduced in the country during the reporting period as compared to the measured REL/RL, if any :
Q3.1.1 | National Forest Reference Emission Level (REL)/Reference Level (RL) defined:
A3.1.1 | N/A
Q3.1.2 | Number of tons reduced during the reporting period as compared to REL/RL:
A3.1.2 | N/A
Amount of non-FCPF investments received under R-PP process:
Q3.1.3 | Source: |  | <Select> | Amount Provided:
A3.1.3.1 | Porgrama Regional Centroamerica y Republica Dominicana REDD+/ CCAD-GIZ | A3.1.4.1 | Currency | 100000
A3.1.3.2 | free text | A3.1.4.2 | Currency
A3.1.3.3 | FAO | A3.1.4.3 | $ - USD | 5000
Amount of non-FCPF investments received for implementation of ER Programs (e.g. FIP, bilateral donors, private sector), if relevant:
| Source: |  | <Select> | Amount Provided:
Currency
Currency
Currency
Currency
Currency
Level of multi-stakeholder participation and engagement in decision making processes related to emission reductions and forest resource management:
Please describe the process of engagement and consultation implemented, including describing the level of participation and engagement for the following stakeholder categories: Government Agencies, Indigenous Peoples, Other forest-dependent peoples, Women, Youth, Civil Society Organizations, Private Entities, Donors, and Others
A la fecha se ha trabajado con representantes de los Ministerios de Agricultura y Ganadería, Instituto Nacional de Estudios Territoriales (INETER), Instituto Nacional Forestal (INAFOR) Fondo para el Desarrollo Forestal (FONADEFO) Autoridades de los pueblos indigenas (Gobernadores, Presidentes Territoriales y Miembros del Consejo Regional de la Costa Caribe y Pacifico, asi como con los Financiadores.(GIZ, FAO, PNUD) . La participacion de estas diiferentes entidades se ha estructurado en tres niveles : Politico, Tecnico y Sociedad Civil. En cada uno de estos niveles la participación a sido crucial desde la construcción de los instrumentos base (Manual Operativo del proyecto, Presupuesto, POA y la priorización de las acciones relevantes en los territorios. También han participado de la presentación y defensa del proceso del R-PP y en los diferentes foros internacionales de pueblos indigenas contando la experiencia de trabajo en Nicaragua.
Nb. and type of policy reforms underway or completed complying to REDD+ standards, if any (FCPF M&E Framework Indicator I.3.B.):
Number of policy reforms during the reporting period that are: <Select from dropdown list>
| Underway: |  | 1 | N/A
|  |  | 2 | N/A
#
#
| Completed: |  | 1 | N/A
#
#
Please describe these policy reforms:
N/A
3.2 PROGRESS AT THE OUTPUT and OUTCOME LEVEL (if any data available)
3.2.1. REDD Readiness Progress
OUTCOME LEVEL
As a synthesis of the following output level assessments, please briefly describe here the progress made during the reporting period in developing the country Readiness Package (FCPF M&E Framework Indicator 1.A.):
Briefly describe progress made during the reporting period in developing the country Readiness Package:
Se estan creando las condiciones para habilitación de la Unidad Coordinadora del Proyecto, se ha contratado el 75% de la plantilla prevista, se tiene presencia en la Costa Caribe, mediante la asistencia de un Coordinador Territorial que funciona como enlace entre la Secretaria de Recursos Naturales (SERENA, Delegacion del MARENA GRACCN y GRACCS y los representantes de los Gobiernos Territoriales (GTI). Se esta preparando los TDR : a) para el Diagnostico de Marco Legal , de Politicas y de Gobernanza. y b) Elaboracion de un Manual de Funciones que guie el accionar de los tres niveles de diálogo y consulta. Se inicia el proceso de inducción con participación de los involucrados de los tres niveles ENDE-REDD+ para ello se han desarrollado 5 sesiones de trabajo 2 en Managua con los Niveles I y II y 1 en la RACCS, 1 en la RACCN y 1 en Masaya con los GTI y Pueblos Indígenas del Pacifico Centro Norte.
Se esta preparando los TDR para iniciar el desarrollo del proceso de establecimiento de los niveles de referencia y linea base de la deforestación y emisiones mediante la contratación de servicios a terceros (INETER). Se inicia el proceso de inducción con participación de los involucrados de los tres niveles ENDE-REDD+ para ello se han desarrollado 4 sesiones de trabajo 2 en Managua con los Niveles I y II y 2 en la RACCS con autoridades territoriales.
Please indicate which of your country R-PP components and sub-components have received support from FCPF through the Readiness Preparation Grant (>3.4 million USD)
| Component |  |  | Support from FCPF (Yes/No)
Component 1. Readiness Organization and Consultation
| 1a. National REDD+ Management Arrangements |  |  | Yes
| 1b. Consultation, Participation, and Outreach |  |  | Yes
Component 2. REDD+ Strategy Preparation
| 2a. Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance |  |  | Yes
| 2b. REDD+ Strategy Options |  |  | Yes
| 2c. Implementation Framework |  |  | Yes
| 2d. Social and Environmental Impacts |  |  | Yes
Component 3. REL/RL
| 3. Reference Emissions Level/Reference Levels |  |  | Yes
Component 4. Monitoring Systems for Forests and Safeguards
| 4a. National Forest Monitoring System |  |  | Yes
| 4b. Information System for Multiple Benefits, Other Impacts, Governance, and Safeguards |  |  | Yes
Level of implementation of R-PP as a whole:
| Please describe the current R-PP implementation stage: | % Completed:
1.- Creación de la Unidad Coordinadora del Proyecto (75% del personal previsto inicialmente contratado). 2.- Creacion de base logistica de soporte se ha contratado la adquisición de 3 vehiculos y 3 motocicletas 100% Y los Equipos informáticos en proceso previo a la adjudicación. 3.- Se dio Inicio al proceso de inducción del equipo técnico involucrado en el Proyecto y diseminacion de informacion propia del proyecto en los tres (3) niveles de diálogo. 4. Se esta trabajando en la realización de un diagnóstico de la plataforma tecnologica sobre la cual se basara el Sistema Nacional de Monitoreo de Bosque. Se capacito al equipo técnico interinstitucional que elaborara el mapa de uso actual del suelo, el cual se utilizara como insumo para el establecimiento de los niveles de referencia de emisiones y linea de base de la deforestación. 5. Iniciado el proceso de clasificación de imagenes de satelite RapidEye para elaboración de mapa de uso actual. 6. Iniciado el proceso de inducción dirigido a los equipos técnicos, Gobiernos territoriales indígenas de la Costa Caribe, Pueblos indígenas del Pacifico Centro Norte, así como con las autoridades de gobiernos regionales de la Costa Caribe, con los cuales se desarollaran los instrumentos de gestión del proyecto (POA) del año 2015. El R-PP en su conjunto esta en un 10% de ejecución, esperando en un lapso no mayor a los seis meses tener avances sustantivos desde el punto de vista técnico y financiero.
Level of achievement of planned milestones according to approved FCPF-financed Readiness Fund Grant (>3.8 million USD) (FCPF M&E Framework 1.3b):
| Planned Milestones: Hitos previstos | Level of Achievement: Nivel de logro |  | Tracking:
| 1. Establecidos los marcos organizativos y de consulta del proceso de gobernanza nacional. 2. Elaborada la Estrategia Nacional ENDE-REDD+. | Bajo |  | 3
| 3. Iniciado el proceso de elaboración de los escenarios de referencia. 4.Elaborado el diseño del Sistema Nacional de Monitoreo de los bosques | Bajo
| 5.Diseñado un programa de Monitoreo Marco de Evaluación del proyecto. | Bajo
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Group Box 124
Next Page
Previous Page

## Sheet 3 - Disbursements 3.2.2
3.2.1. CONTINUED Disbursement rate of FCPF-financed Readiness Fund Grant (>3.4 million USD), in %
RF Grant - disbursement rate compared to planned disbursement rate
Disbursement rate of FCPF-financed Readiness Fund Grant (>3.4 million USD), in percentage:
| Select Actual Disbursement Rate | Tracking | 3
RF Grant - actual disbursement rate compared to planned disbursement rate | 10% | 3
Disbursement rate of Total R-PP Budget in percentage:
| Select Actual Disbursement Rate | Tracking
R-PP Budget - disbursement rate v planned disbursement rate | 10% | 3
Next Page
Previous Page
Up to 10% variance with plans
Between 10 and 25% variance
Between 25 and 40% variance
More than 40% variance
Not Applicable
Up to 10% variance with plans
Between 10 and 25% variance
Between 25 and 40% variance
More than 40% variance
Not Applicable

## Sheet 4 3.2.1 cont'd
3.2.1. REDD Progress Levels - Continued
Countries are expected to provide data on the overall level of achievement of planned milestones as defined in their Readiness Preparation Grant Agreement, and, if applicable, on their Supplementary Grant Agreement (additional grant of up to $5 million). Under their Preparation Readiness Grant Agreement (>3.4 million USD), Countries should provide data on (i) the support to the Coordination of the REDD+ Readiness Process and Multi-Stakeholder Consultations; (ii) the contribution to the Design of a National REDD+ Strategy; and (iii) the preparation of a National Reference Scenario for REDD+ The level of achievement of planned milestones according to the Readiness grant will be summarized through progress scores related to the synthesis of an overall achievement. This is qualitatively expressed with a four-color ‘traffic light’ scale and then explained. In case the assessment is not applicable, “Non Applicable” can be selected. The level of achievement of planned milestones per R-PP component should be self-assessed and reported, as well as summarized through progress scores related to the synthesis of this overall achievement, qualitatively expressed on a four-color ‘traffic light’ scale and then briefly explained. In case the assessment is not applicable, a fifth color scale ‘Non Applicable’ can be selected. This ‘traffic light’ scale is based on the system contained in the R-Package Assessment Framework, The R-Package assessment criteria are included to assist countries identify, plan and track their readiness preparations progress with the core aspects and desired outcomes of readiness preparation activities as contained in R-Package Assessment Framework.
Sub-Component 1a | Overall Progress |  | Progress Against Annual Targets |  | Tracking* | 3
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target
1a - National REDD+ Management Arrangements Purpose: setting-up national readiness management arrangements to manage and coordinate the REDD-plus readiness activities whilst mainstreaming REDD-plus into broader strategies Assessment Criteria: (i) accountability and transparency; (ii) operating mandate and budget; (iiI) multi-sector coordination mechanisms and cross-sector collaboration; (iv) technical supervision capacity; (v) funds management capacity; (vi) feedback and grievance redress mechanism | Elaborado el Manual de Funciones de los tres niveles | en proceso | Documento de Manual de Funciones de los tres Niveles |  | 3
| Establecida Unidad de Coordinación del proyecto | en proceso | Unidad de Coordinación del Proyecto Conformada
3
Sub-Component 1b | Overall Progress |  | Progress Against Annual Targets |  | Tracking
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 3
1b – Consultation, Participation, and Outreach Purpose: broad consultation with and participation of key stakeholders for future REDD+ programs, to ensure participation of different social groups, transparency and accountability of decision-making Assessment Criteria: (i) participation and engagement of key stakeholders; (ii) consultation processes; (iii) information sharing and accessibility of information; (iv) implementation and public disclosure of consultation outcomes | Mecanismo de Intercambio de Información y Dialogo. | en proceso | Mecanismo de Información y Dialogo Funcionando |  | 3
| Proceso de Consulta y participación con Pueblos Indígenas de la Costa Caribe | en proceso | Creadas las condiciones para el proceso de consulta en la Costa Caribe.
| Diseñado mecanismos de queja y resolución de Conflictos y una estrategia de comunicación. | en proceso | Mecanismo de quejas y resolución de conflictos y Estrategia de comunicación Funcionando
Sub-Component 2a | Overall Progress |  | Progress Against Annual Targets |  | Tracking
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target
2a: Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance Purpose: identify key drivers of deforestation and/or forest degradation, as well as activities concerning conservation, sustainable forest management, and enhancement of forest carbon stocks Assessment Criteria: (i) assessment and analysis; (ii) prioritization of direct and indirect drivers/barriers to forest enhancement; (iii) links between drivers/barriers and REDD+ activities; (iv) actions plans to address natural resource rights, land tenure, governance; (v) implications for forest law and policy | Elaborado documento de Analisis de las Causas directas e indirectas de la degradación y deforestación | en proceso | Documento Analisis de las Causas directas e indirectas de la degradación y deforestación |  | 4 | 4
| Definidos los lineamientos estrategicos y su marco de implementación | en proceso | lineamientos estrategicos y su marco de implementación
4
Sub-Component 2b | Overall Progress |  | Progress Against Annual Targets |  | Tracking
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
2b: REDD+ Strategy Options Purpose: Develop a set of policies and programs for addressing the drivers of deforestation and/or forest degradation Assessment Criteria: (i) selection and prioritization of REDD+ strategy options; (ii) feasibility assessment; (iii) implications for strategy options on existing sectoral policies | Preparado un documento borrador avanzado de la Estrategia |  | Documento borrador avanzado de la Estrategia |  | 4 | 0
0
0
0
0
0
0
0
Sub-Component 2c | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
2c: Implementation Framework Purpose: Set out credible and transparent institutional, economic, legal and governance arrangements necessary to implement REDD+ strategy options Assessment Criteria: (i) adoption and implementation of legislation/regulations; (ii) guidelines for implementation; (iii) benefit sharing mechanism; (iv) national REDD+ registry and system monitoring REDD+ activities |  |  |  |  | 4 | 0
0
0
0
0
0
0
0
Sub-Component 2d | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
2d: Social and Environmental Impacts Purpose: Ensure compliance with the Common Approach and prepare a country specific Environmental and Social Management Framework (ESMF) Assessment Criteria: (i)) analysis of social and environmental safeguard issues; (ii) REDD+ strategy design with respect to impacts; (iii) Environmental and Social Management Framework | Iniciado el proceso de Evaluación Ambiental y Social Estrategica (SESA) y se ha elaborado el borrador del Marco de estión Ambiental y Social (ESMF). | en proceso | Evaluación Ambiental y Social Estrategica (SESA) y borrador del Marco de estión Ambiental y Social (ESMF) elaborados. |  | 4 | 0
0
0
0
0
0
0
0
0
Component 3 | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
R-PP Component 3 - Reference Emissions Level/Reference Levels Purpose: Development of the general approach to establish a REL/RL Assessment Criteria: (i) demonstration of methodology; (ii) use of historical data, and adjusted for national circumstances; (iii) technical feasibility of the methodological approach, and consistency with UNFCCC/IPCC guidance and guidelines | elaborado Documento de Evaluación de la información y las capacidades existentes en las instituciones… |  | Documento de Evaluación de la información y las capacidades existentes en las instituciones… |  | 4 | 0
| Elaborado documento para fortalecimiento de las capacidades de las instituciones para desarrollar escenarios de referencia de la deforestación y emisiones de carbono. |  | Documento para fortalecimiento de las capacidades de las instituciones para desarrollar escenarios de referencia de la deforestación y emisiones de carbono. |  |  | 0
| Desarrollada una metodología y protocolo para un escenario de referencia y línea de base de la deforestación y Emisiones. |  | Metodología y protocolo para un escenario de referencia y línea de base de la deforestación y Emisiones. |  |  | 0
0
0
0
0
Sub-Component 4a | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
4a: National Forest Monitoring System Purpose: Design and develop an operational forest monitoring system and describe the approach to enhance the system over time Assessment Criteria: (i) documentation of monitoring approach; (ii) demonstration of early implementation; (iii) institutional arrangements and capacities- Forests | Diseñado un sistema nacional de monitoreo de bosques multipropósito |  | Sistema nacional de monitoreo de bosques multipropósito |  | 4 | 0
0
0
0
0
0
0
#REF!
0
Sub-Component 4b | Overall Progress |  | Progress Against Annual Targets |  | Tracking | 0
| Planned Milestones | Cumulative Progress Towards Milestones | Expected Annual Target | Achievements of the Annual Target |  | 4
4b: Information System for Multiple Benefits, Other Impacts, Governance, and Safeguards Purpose: Specify the non-carbon aspects prioritized for monitoring by the country Assessment Criteria: (i) identification of relevant non-carbon aspects, and social and environmental issues; (ii) monitoring, reporting and information sharing; (iii) Institutional arrangements and capacities – Safeguards | Fortalecidas las capacidades en monitoreo de las instituciones vinculadas a… |  | Fortalecidas las capacidades en monitoreo de las instituciones vinculadas a… |  | 4 | 0
0
0
*This ‘traffic light’ scale is based on the system contained in the R-Package Assessment Framework, The R-Package assessment criteria are included to assist countries identify, plan and track their readiness preparations progress with the core aspects and desired outcomes of readiness preparation activities as contained in R-Package Assessment Framework.
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Next Page
Previous Page
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable

## Sheet 5 - 3.2.3 - 3.2.4
3.2.3. Engagement of stakeholders to sustain or enhance livelihoods of local communities and to conserve biodiversity within the approach to REDD+
OUTCOME LEVEL
As a synthesis of the following output level assessments, please describe indicators related to biodiversity conservation and forest community livelihood development included in the ER Program if relevant (FCPF M&E Framework indicator 3.A.):
Amount provided: |  | Currency
Please describe how these funds target biodiversity and forest community livelihood development: |  | Free Text n / a
Please provide relevant examples on the inherent social and biodiversity benefits of REDD+, if relevant (FCPF M&E Framework Indicator 3.B.):
1
Examples of inherent social and biodiversity benefits of REDD+:
Free textn / a
OUTPUT LEVEL -Nivel de salida
Number of examples of actions where Ips, CSOs, and local communities participate actively, if relevant (FCPF M&E Framework 3.2.a.):
#: | Please describe these actions on enhanced livelihoods and BD conservation, and restoration where Ips, CSO, and local communities participate actively:
Number of IPs, REDD Country CSO representatives (men/women) having been successfully trained by FCPF training programs (FCPF M&E Framework 3.1.b.):
Please list the training(s) conducted: | Duration (#of days) | # of participants |  | Rating
|  | # of men | # of women
Free text |  |  |  | 4
Frequency of meetings of stakeholder engagement platforms (FCPF M&E Framework 3.2.a.):
Frequency: |  |  | Rating
4
Does your country R-Package (within the national REDD+ strategies and the monitoring systems) and/or ER Program include activities aiming at maintaining or enhancing livelihoods of local communities (FCPF M&E Framework 3.2.b.):
Yes/No: | Please describe these activities aiming at maintaining or enhancing livelihoods of local communities:
Yes | Estamos en proceso de planificación para el establecimiento del sistema de monitoreo y de los mismos niveles de referencia. Ahí seran incluidas estas actividades destinadas a mantener o mejorar los medios de subsistencia de las comunidades locales.
Does your country R-Package (within the national REDD+ strategies and the monitoring systems) and/or ER Program include activities aiming at conserving biodiversity (FCPF M&E Framework 3.2.c.)?
No | Please describe these activities aiming at conserving biodiversity:
Yes | Estamos en proceso de planificación para el establecimiento del sistema de monitoreo y de los mismos niveles de referencia. Ahí seran incluidas estas actividades destinadas a conservar la biodiversidad.
Does your country R-Package and/or ER Program include SESA, an operational Grievance Mechanism, and an ESMF that captures SESA results (FCPF M&E Framework 3.2.d.)?
No | Please describe these activities aiming at conserving biodiversity:
No | En proceso de contratcion del Especialista SESA
3.2.4 Knowledge Sharing
Has your country developed and published REDD+ knowledge products with FCPF support?
Yes/No: | If yes, please provide a list of the published REDD+ knowledge products if any, during the reporting period:
No | 1
2
3
4
…
How many people have been reached by these knowledge products, if any?
Overall number by product: | Please provide a list of the published REDD+ knowledge products if any, during the reporting period:
Knowledge Product 1:
# Total People Reached |  |  |  | 0
# of Men
# of Women
Knowledge Product 2:
# Total People Reached |  |  |  | 0
# of Men
# of Women
Knowledge Product 3:
# Total People Reached |  |  |  | 0
# of Men
# of Women
Knowledge Product 4:
# Total People Reached |  |  |  | 0
# of Men
# of Women
Have some experts of your country participated in any South-South learning activities? If yes, how many?
Yes/No | List the South-South Exchanges: |  | # Men | # Women
Yes/No | México |  | 1
Yes/No
Yes/No
Yes/No
Next Page
Previous Page
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable

## Sheet 6 - Disbursements 3.2.2
3.2.2. Key Elements of performance based payment systems for emission reductions generated from REDD+ activities
OUTCOME LEVEL
As a synthesis of the following output level assessments, please briefly specify:
Are carbon accounting, programmatic elements and pricing operating as planned in your pilot, if relevant? |  |  | 15
Tracking
Free text |  |  |  | 5
Is the benefit sharing scheme being implemented according to plans within your pilot, if relevant?
Tracking
Free text |  |  |  | 5
Percentage and/or amount of monetary benefits shared with beneficiaries in approved pilot, if relevant?
Tracking
Free text |  |  |  | 5
OUTPUT LEVEL
As a synthesis of the following output level assessments, please briefly specify:
Has your country submitted early ideas or ER-Program to the Carbon Fund and or others?
Yes/No | Please briefly describe the content of these early ideas or ER-Program:
Yes/No | Para llenar por Javier Gutiérrez
Has your country signed an ERPA?
Has your country submitted early ideas or ER-Program to the Carbon Fund and or others?
Yes/No | Please briefly describe the content of this ERPA:
Yes/No | Para llenar por Javier Gutiérrez
Amount and date of disbursements for ER Program according to plans, if relevant:
Date format: | mm/dd/yyyyy |  | <Select>
Date: |  | Amount provided: | Currency
Date: |  | Amount provided: | Currency
Date: |  | Amount provided: | Currency
Next Page
Previous Page
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable
Significant progress
Progressing well, further development required
Further development required
Not yet demonstrating progress
Not Applicable

## Sheet 7 Sections 4 -5 I, C,R
4. Issues Challenges and Risks
This section should present any problems, difficulties or constraints faced by the country in making progress towards the intended REDD+ results (outputs, outcomes and possible impacts), the main causes and their expected effect on the work plan. Actions that have been taken to overcome or manage these constraints/flaws/problems identified should be stated. Each problem/constraint should be stated as a separate point, along with associated proposed changes in work planning for the next six month/year to address it, as relevant.
Issue, Challenge, Risk | Actions to overcome, Adjustments to plan
Institutional | Mejorar la sistematización y agiliazar la aprobación de los instrumentos TdRs para el desarrollo de las actividades.
Operational | Reducir los tiempos de las No objeciones
Institutional | Culminar con la contratación de todo el equipo de consultores
5. Main Lessons Learned
This section should be used to provide information on important lessons learnt since the beginning of the readiness process. As this is a semi-annual report, it is expected that this section will be fairly substantial, making reference to different lessons learning documents, and/or events developed and dealing with issues of particular interest with respect to readiness of carbon funding under REDD+.
Free text lecciones aprendidas Tiempo de arranque de un proyecto se extiende en la medida en que no se cuenta con el personal minimo requerido para iniciar la operación. Un proyecto que no tiene la no objeción a los instrumentos financieros y fiduciarios, el manual operativo del proyecto y otros no puede iniciar operaciones. Tiempo de firma de convenio de la donación se extendio más de lo usual ocasionando junto con lo anterior un defase de casi un año.
Complete
Previous Page

## REF (hidden)
a
5 | Significant progress |  |  | Actual Disbursement Rate |  | Issue_Challenge_Risk
4 | Progressing well, further development required |  |  | 10% |  | Operational |  | Code | Combo | Country
3 | Further development required |  |  | 40% |  | Institutional |  | £ | £ - Pound | Pound
2 | Not yet demonstrating progress |  |  | 70% |  | Financial |  | € | € - Euro | Euro
1 | Non Applicable |  |  | 85% |  | Other |  | $ | $ - USD | USD
[8 empty] | ¥ | ¥ - Yen | Yen
[8 empty] | AED | AED - United Arab Emirates Dirham | United Arab Emirates Dirham
|  | Page | Characters |  |  |  |  | AFN | AFN - Afghanistan Afghani | Afghanistan Afghani
| YesNo | page | 32000 |  |  |  |  | ALL | ALL - Albania Lek | Albania Lek
| Yes | halfpage | 1600 |  |  |  |  | AMD | AMD - Armenia Dram | Armenia Dram
| No | [6 empty] | ANG | ANG - Netherlands Antilles Guilder | Netherlands Antilles Guilder
[8 empty] | AOA | AOA - Angola Kwanza | Angola Kwanza
[8 empty] | ARS | ARS - Argentina Peso | Argentina Peso
[8 empty] | AUD | AUD - Australia Dollar | Australia Dollar
[8 empty] | AWG | AWG - Aruba Guilder | Aruba Guilder
[8 empty] | AZN | AZN - Azerbaijan New Manat | Azerbaijan New Manat
[8 empty] | BAM | BAM - Bosnia and Herzegovina Convertible Marka | Bosnia and Herzegovina Convertible Marka
[8 empty] | BBD | BBD - Barbados Dollar | Barbados Dollar
[8 empty] | BDT | BDT - Bangladesh Taka | Bangladesh Taka
[8 empty] | BGN | BGN - Bulgaria Lev | Bulgaria Lev
[8 empty] | BHD | BHD - Bahrain Dinar | Bahrain Dinar
[8 empty] | BIF | BIF - Burundi Franc | Burundi Franc
[8 empty] | BMD | BMD - Bermuda Dollar | Bermuda Dollar
[8 empty] | BND | BND - Brunei Darussalam Dollar | Brunei Darussalam Dollar
[8 empty] | BOB | BOB - Bolivia Boliviano | Bolivia Boliviano
[8 empty] | BRL | BRL - Brazil Real | Brazil Real
[8 empty] | BSD | BSD - Bahamas Dollar | Bahamas Dollar
[8 empty] | BTN | BTN - Bhutan Ngultrum | Bhutan Ngultrum
[8 empty] | BWP | BWP - Botswana Pula | Botswana Pula
[8 empty] | BYR | BYR - Belarus Ruble | Belarus Ruble
[8 empty] | BZD | BZD - Belize Dollar | Belize Dollar
[8 empty] | CAD | CAD - Canada Dollar | Canada Dollar
[8 empty] | CDF | CDF - Congo/Kinshasa Franc | Congo/Kinshasa Franc
[8 empty] | CHF | CHF - Switzerland Franc | Switzerland Franc
[8 empty] | CLP | CLP - Chile Peso | Chile Peso
[8 empty] | CNY | CNY - China Yuan Renminbi | China Yuan Renminbi
[8 empty] | COP | COP - Colombia Peso | Colombia Peso
[8 empty] | CRC | CRC - Costa Rica Colon | Costa Rica Colon
[8 empty] | CUC | CUC - Cuba Convertible Peso | Cuba Convertible Peso
[8 empty] | CUP | CUP - Cuba Peso | Cuba Peso
[8 empty] | CVE | CVE - Cape Verde Escudo | Cape Verde Escudo
[8 empty] | CZK | CZK - Czech Republic Koruna | Czech Republic Koruna
[8 empty] | DJF | DJF - Djibouti Franc | Djibouti Franc
|  |  | list of countries: |  | Argentina |  |  | DKK | DKK - Denmark Krone | Denmark Krone
[5 empty] | Bolivia |  |  | DOP | DOP - Dominican Republic Peso | Dominican Republic Peso
[5 empty] | Cambodia |  |  | DZD | DZD - Algeria Dinar | Algeria Dinar
[5 empty] | Cameroon |  |  | EGP | EGP - Egypt Pound | Egypt Pound
[5 empty] | CAR |  |  | ERN | ERN - Eritrea Nakfa | Eritrea Nakfa
[5 empty] | Chile |  |  | ETB | ETB - Ethiopia Birr | Ethiopia Birr
[5 empty] | Colombia |  |  | EUR | EUR - Euro Member Countries | Euro Member Countries
[5 empty] | Costa Rica |  |  | FJD | FJD - Fiji Dollar | Fiji Dollar
[5 empty] | DR Congo |  |  | FKP | FKP - Falkland Islands (Malvinas) Pound | Falkland Islands (Malvinas) Pound
[5 empty] | El Salvador |  |  | GBP | GBP - United Kingdom Pound | United Kingdom Pound
[5 empty] | Ethiopia |  |  | GEL | GEL - Georgia Lari | Georgia Lari
[5 empty] | Gabon |  |  | GGP | GGP - Guernsey Pound | Guernsey Pound
[5 empty] | Ghana |  |  | GHS | GHS - Ghana Cedi | Ghana Cedi
[5 empty] | Guatemala |  |  | GIP | GIP - Gibraltar Pound | Gibraltar Pound
[5 empty] | Guyana |  |  | GMD | GMD - Gambia Dalasi | Gambia Dalasi
[5 empty] | Honduras |  |  | GNF | GNF - Guinea Franc | Guinea Franc
[5 empty] | Indonesia |  |  | GTQ | GTQ - Guatemala Quetzal | Guatemala Quetzal
[5 empty] | Kenya |  |  | GYD | GYD - Guyana Dollar | Guyana Dollar
[5 empty] | Lao PDR |  |  | HKD | HKD - Hong Kong Dollar | Hong Kong Dollar
[5 empty] | Liberia |  |  | HNL | HNL - Honduras Lempira | Honduras Lempira
[5 empty] | Madagascar |  |  | HRK | HRK - Croatia Kuna | Croatia Kuna
[5 empty] | Mexico |  |  | HTG | HTG - Haiti Gourde | Haiti Gourde
[5 empty] | Mozambique |  |  | HUF | HUF - Hungary Forint | Hungary Forint
[5 empty] | Nepal |  |  | IDR | IDR - Indonesia Rupiah | Indonesia Rupiah
[5 empty] | Nicaragua |  |  | ILS | ILS - Israel Shekel | Israel Shekel
[5 empty] | Panama |  |  | IMP | IMP - Isle of Man Pound | Isle of Man Pound
[5 empty] | PNG |  |  | INR | INR - India Rupee | India Rupee
[5 empty] | Paraguay |  |  | IQD | IQD - Iraq Dinar | Iraq Dinar
[5 empty] | Peru |  |  | IRR | IRR - Iran Rial | Iran Rial
[5 empty] | Republic of Congo |  |  | ISK | ISK - Iceland Krona | Iceland Krona
[5 empty] | Suriname |  |  | JEP | JEP - Jersey Pound | Jersey Pound
[5 empty] | Tanzania* |  |  | JMD | JMD - Jamaica Dollar | Jamaica Dollar
[5 empty] | Thailand |  |  | JOD | JOD - Jordan Dinar | Jordan Dinar
[5 empty] | Uganda |  |  | JPY | JPY - Japan Yen | Japan Yen
[5 empty] | Vanuatu |  |  | KES | KES - Kenya Shilling | Kenya Shilling
[5 empty] | Vietnam |  |  | KGS | KGS - Kyrgyzstan Som | Kyrgyzstan Som
[8 empty] | KHR | KHR - Cambodia Riel | Cambodia Riel
[8 empty] | KMF | KMF - Comoros Franc | Comoros Franc
[8 empty] | KPW | KPW - Korea (North) Won | Korea (North) Won
[8 empty] | KRW | KRW - Korea (South) Won | Korea (South) Won
[8 empty] | KWD | KWD - Kuwait Dinar | Kuwait Dinar
[8 empty] | KYD | KYD - Cayman Islands Dollar | Cayman Islands Dollar
[8 empty] | KZT | KZT - Kazakhstan Tenge | Kazakhstan Tenge
[8 empty] | LAK | LAK - Laos Kip | Laos Kip
[8 empty] | LBP | LBP - Lebanon Pound | Lebanon Pound
[8 empty] | LKR | LKR - Sri Lanka Rupee | Sri Lanka Rupee
[8 empty] | LRD | LRD - Liberia Dollar | Liberia Dollar
[8 empty] | LSL | LSL - Lesotho Loti | Lesotho Loti
[8 empty] | LTL | LTL - Lithuania Litas | Lithuania Litas
[8 empty] | LVL | LVL - Latvia Lat | Latvia Lat
[8 empty] | LYD | LYD - Libya Dinar | Libya Dinar
[8 empty] | MAD | MAD - Morocco Dirham | Morocco Dirham
[8 empty] | MDL | MDL - Moldova Leu | Moldova Leu
[8 empty] | MGA | MGA - Madagascar Ariary | Madagascar Ariary
[8 empty] | MKD | MKD - Macedonia Denar | Macedonia Denar
[8 empty] | MMK | MMK - Myanmar (Burma) Kyat | Myanmar (Burma) Kyat
[8 empty] | MNT | MNT - Mongolia Tughrik | Mongolia Tughrik
[8 empty] | MOP | MOP - Macau Pataca | Macau Pataca
[8 empty] | MRO | MRO - Mauritania Ouguiya | Mauritania Ouguiya
[8 empty] | MUR | MUR - Mauritius Rupee | Mauritius Rupee
[8 empty] | MVR | MVR - Maldives (Maldive Islands) Rufiyaa | Maldives (Maldive Islands) Rufiyaa
[8 empty] | MWK | MWK - Malawi Kwacha | Malawi Kwacha
[8 empty] | MXN | MXN - Mexico Peso | Mexico Peso
[8 empty] | MYR | MYR - Malaysia Ringgit | Malaysia Ringgit
[8 empty] | MZN | MZN - Mozambique Metical | Mozambique Metical
[8 empty] | NAD | NAD - Namibia Dollar | Namibia Dollar
[8 empty] | NGN | NGN - Nigeria Naira | Nigeria Naira
[8 empty] | NIO | NIO - Nicaragua Cordoba | Nicaragua Cordoba
[8 empty] | NOK | NOK - Norway Krone | Norway Krone
[8 empty] | NPR | NPR - Nepal Rupee | Nepal Rupee
[8 empty] | NZD | NZD - New Zealand Dollar | New Zealand Dollar
[8 empty] | OMR | OMR - Oman Rial | Oman Rial
[8 empty] | PAB | PAB - Panama Balboa | Panama Balboa
[8 empty] | PEN | PEN - Peru Nuevo Sol | Peru Nuevo Sol
[8 empty] | PGK | PGK - Papua New Guinea Kina | Papua New Guinea Kina
[8 empty] | PHP | PHP - Philippines Peso | Philippines Peso
[8 empty] | PKR | PKR - Pakistan Rupee | Pakistan Rupee
[8 empty] | PLN | PLN - Poland Zloty | Poland Zloty
[8 empty] | PYG | PYG - Paraguay Guarani | Paraguay Guarani
[8 empty] | QAR | QAR - Qatar Riyal | Qatar Riyal
[8 empty] | RON | RON - Romania New Leu | Romania New Leu
[8 empty] | RSD | RSD - Serbia Dinar | Serbia Dinar
[8 empty] | RUB | RUB - Russia Ruble | Russia Ruble
[8 empty] | RWF | RWF - Rwanda Franc | Rwanda Franc
[8 empty] | SAR | SAR - Saudi Arabia Riyal | Saudi Arabia Riyal
[8 empty] | SBD | SBD - Solomon Islands Dollar | Solomon Islands Dollar
[8 empty] | SCR | SCR - Seychelles Rupee | Seychelles Rupee
[8 empty] | SDG | SDG - Sudan Pound | Sudan Pound
[8 empty] | SEK | SEK - Sweden Krona | Sweden Krona
[8 empty] | SGD | SGD - Singapore Dollar | Singapore Dollar
[8 empty] | SHP | SHP - Saint Helena Pound | Saint Helena Pound
[8 empty] | SLL | SLL - Sierra Leone Leone | Sierra Leone Leone
[8 empty] | SOS | SOS - Somalia Shilling | Somalia Shilling
[8 empty] | SPL* | SPL* - Seborga Luigino | Seborga Luigino
[8 empty] | SRD | SRD - Suriname Dollar | Suriname Dollar
[8 empty] | STD | STD - São Tomé and Príncipe Dobra | São Tomé and Príncipe Dobra
[8 empty] | SVC | SVC - El Salvador Colon | El Salvador Colon
[8 empty] | SYP | SYP - Syria Pound | Syria Pound
[8 empty] | SZL | SZL - Swaziland Lilangeni | Swaziland Lilangeni
[8 empty] | THB | THB - Thailand Baht | Thailand Baht
[8 empty] | TJS | TJS - Tajikistan Somoni | Tajikistan Somoni
[8 empty] | TMT | TMT - Turkmenistan Manat | Turkmenistan Manat
[8 empty] | TND | TND - Tunisia Dinar | Tunisia Dinar
[8 empty] | TOP | TOP - Tonga Pa'anga | Tonga Pa'anga
[8 empty] | TRY | TRY - Turkey Lira | Turkey Lira
[8 empty] | TTD | TTD - Trinidad and Tobago Dollar | Trinidad and Tobago Dollar
[8 empty] | TVD | TVD - Tuvalu Dollar | Tuvalu Dollar
[7 empty] | $ | TWD | TWD - Taiwan New Dollar | Taiwan New Dollar
[8 empty] | TZS | TZS - Tanzania Shilling | Tanzania Shilling
[8 empty] | UAH | UAH - Ukraine Hryvna | Ukraine Hryvna
[8 empty] | UGX | UGX - Uganda Shilling | Uganda Shilling
[8 empty] | USD | USD - United States Dollar | United States Dollar
[8 empty] | UYU | UYU - Uruguay Peso | Uruguay Peso
[8 empty] | UZS | UZS - Uzbekistan Som | Uzbekistan Som
[8 empty] | VEF | VEF - Venezuela Bolivar | Venezuela Bolivar
[8 empty] | VND | VND - Viet Nam Dong | Viet Nam Dong
[8 empty] | VUV | VUV - Vanuatu Vatu | Vanuatu Vatu
[8 empty] | WST | WST - Samoa Tala | Samoa Tala
[8 empty] | XAF | XAF - Communauté Financière Africaine (BEAC) CFA Franc BEAC | Communauté Financière Africaine (BEAC) CFA Franc BEAC
[8 empty] | XCD | XCD - East Caribbean Dollar | East Caribbean Dollar
[8 empty] | XDR | XDR - International Monetary Fund (IMF) Special Drawing Rights | International Monetary Fund (IMF) Special Drawing Rights
[8 empty] | XOF | XOF - Communauté Financière Africaine (BCEAO) Franc | Communauté Financière Africaine (BCEAO) Franc
[8 empty] | XPF | XPF - Comptoirs Français du Pacifique (CFP) Franc | Comptoirs Français du Pacifique (CFP) Franc
[8 empty] | YER | YER - Yemen Rial | Yemen Rial
[8 empty] | ZAR | ZAR - South Africa Rand | South Africa Rand | 1
[8 empty] | ZMW | ZMW - Zambia Kwacha | Zambia Kwacha | 2
[8 empty] | ZWD | ZWD - Zimbabwe Dollar | Zimbabwe Dollar | 3
[9 empty] | Other |  | 4
5
[10 empty] | Land Use | 6
[10 empty] | Tenure | 7
Benefit Sharing
Institutional Reforms
Other
10%
40%
60%
80%

## Database (hidden)
Sheet | Participant ID | Partcipant Details | Contact Country | Contact Name 1 | Title 1 | Contact Name 2 | Title 2 | Contact Email | Alternate Email | Contace Telephone | Alternate Telephone | Submission Date
Partcipant | 11111 | 0 | Nicaragua | Zenia Salinas | Punto Focal de la Secretaria de FCPF para Nicaragua | Augusto Garcia | Gerente de Poyecto FCPF por BM como socio ejecutor | agarcia2worldbank.org | 0 | 0 | 0 | 27 de agosto 2014

## Sheet1 (hidden)
Q_ID | Section | Questions | A_ID | Answer
Q1 | 1 | Introduction to the report, its main purpose and sections. Short description of FCPF support in country. | A1
Q2 | 2 | Summary of progress, key achievements with a focus on higher level results and important issues/problems that arose during the reporting period. Highlights of next steps in following period -- key bullets only | A2
Q3