## Slide 1: Update progress on development of ER-Program in Vietnam
Presented at the 6th FCPF Carbon Fund
Washington DC
15-16 March 2013

## Slide 2: Update progress on ER-PIN Preparation
Based on:
ER-PIN Template
Comments from previous meeting in late January 2013

## Slide 3: Overview
Two versions of presentation are prepared: full version and short version
Summary of relevant national commitments, strategies and policies on REDD+
Update information on progress of ER-PIN development

## Slide 4: Check list (1/2)
No. | Required Sections | Progress
1 | Entity responsible for the management of ER Prog | Done
2 | National REDD+ focal point contact information | Done
3 | Partners and other entities involved | Done
4 | ER Program location and lifetime | Significant progress
5 | Description of activities planned under the ER Prog | Significant progress
6 | Consistency with national REDD+ strategy and governance arrangements | Finalizing
7 | Preliminary assessment of SESA and ESMF/safeguards | Significant progress

## Slide 5: Check list (2/2)
No. | Required Sections | Progress
8 | Stakeholder Information Sharing, Consultation, and Participation | Significant progress
9 | Additional Benefits | On-going
10 | Benefit Sharing | On-going
11 | Reference Level and Expected Emission Reductions | Significant progress
12 | Forest Monitoring System | Significant progress
13 | Summary of Progress on REDD+ Readiness | Significant progress
14 | Financing plan | Not started

## Slide 6: 2.1. Formal establishment of joint working team on ER-PIN development
A core working team is established by MARD, consists of members from different Gov agencies and experts; representatives from independent experts, NGOs, international partners are invited to work contribute their knowledge and comments;
The working team is responsible for taking lead in ER-PIN preparation

## Slide 7: 2.2. Intensive stakeholders consultations
In last 3 months, intensive consultations on aspects of ER Prog. and REDD+, have been conducted
Topics: from site selection, institutional setting, coordination mechanism, REDD+ activities, FPIC, GRM, ect.
Types of stakeholders: relevant stakeholders at both national and provincial levels are carried not only with national entities but also with international development partners, projects/progs;
Methods: a step-wise and phased approach, starting from information sharing to joint-decision making through workshops & meetings at national and local levels; and inherited from previous consultations for NRAP, R-PP;
Experience: provision of right information, attraction of interest, building the trust & responsibility, fruitful discussions

## Slide 8: Some consultation events

## Slide 9: Results: Interested of participation and commitment
After Awareness raising and consultation events:
Gov shows its commitment by implementation of relevant policies and considerable investment in forestry, agricultural and rural development to address key driving forces behind forest changes, and provide support for REDD+ readiness preparation (regulations, FMS, DBM, BDS);
28 provinces have sent request to attend the ER Program
Participation of NGOs and international development partners. VNFOREST has signed MOUs with ICRAF, RECOFTC, SNV, national NGOs

## Slide 10: Consultation on criteria of site selection
Cover large forest areas, high potential of emission reduction;
Commitment of local authorities and capacities of relevant stakeholders;
Opportunities of coordination with on-going policies/programs forest protection, reforestation, climate smart agriculture and livelihood improvement funded by Gov or international partners;
Generate co-benefits (biodiversity conservation, improvement of livelihoods of local communities, promotion of FLEGT/VPA and regional cooperation)

## Slide 11: Two options on scale of the ER Program

## Slide 12: Scalable options for ER Program
Option 1: only in the Northern Central Coastal Region (3.4 million ha of forestland, of which 2.8 million ha are forested);
Option 2: ER Program will cover 16 provinces with high potential ER (7 mill. ha of forestland). All these provinces have sent letter of interest and commitment to participate in the Program;
The answer is dependent upon the availability of financial resources

## Slide 13: Scale the ER Program: Option 1

## Slide 14: Information on the proposed ER site
Province | Total area (ha) | Total forested area (ha) | Natural forests (ha) | Plantations (ha) | Forest cover (%) | Population (1.000 pers)
Thanh Hoa | 1,113,194 | 546,095 | 384,146 | 161,949 | 49% | 3406.8
Nghe An | 1,649,181 | 875,312 | 734,515 | 140,797 | 53% | 2917.4
Ha Tinh | 599,718 | 308,082 | 212,884 | 95,198 | 51% | 1228
Quang Binh | 806,527 | 540,118 | 456,537 | 83,581 | 67% | 849.3
Quang Tri | 473,982 | 223,350 | 138,807 | 84,543 | 47% | 600.5
T.Thien Hue | 503,321 | 285,347 | 202,647 | 82,701 | 57% | 1090.9
Total | 5,145,923 | 2,778,304 | 2,129,536 | 648,769 | 54% | 10,092.90

## Slide 15: Discussions on approach and key REDD+ Activities
Landscape-based approach: not only activities within the forestry sector, agricultural and other sector will be taken into account to deliver comprehensive, effective packages for substantial and permanent ER;
Multi-policies and activities will be taken place to effectively address key driving forces behind deforestation and forest degradation, and to accelerate reforestation. It is not wise and practical if only a single REDD+ activity is conducted in a forest stand; Promotion of bundled policies on climate smart agriculture, increase in agr. productivity, poverty alleviation, alternative income generating opt., PES & incentives, forest law enforcement
Mobilization of resources from different sources (GoV budget, private sectors, ODA, contribution of local stakeholders)

## Slide 16: Proposed key REDD+ Activities
Avoided deforestation and forest degradation
  Prevention of conversion of forests into agriculturally cultivated land
  Protection against illegal logging and promotion of SFM
  Forest fire prevention; Modern wood processing industry, sustainable use of timber and NTFPs, firewood
Enhancement of forest carbon stocks:
  Assisted natural regeneration of forests; Restoration of heavily degraded forest land with agroforestry
  Plantations but promotion of planting big timber (long rotation) and native species

## Slide 17: How to do?
Foundations: NCCS, NGGS, NRAP, NAP on FPD
Development the ER Prog.
Each province will develop its REDD+ Action Plan (RAP); REDD+ activities should be mainstreamed into provincial Socio-economic and Environment Development Master Plan, and consistent with National REDD+ Action Program;

## Slide 18: Discussions on Institutional arrangement for ER Prog.
How the ER program will be implemented in line with NRAP and other national policies?
REDD+ = cross-sectors and multi-policies – should not create a totally new institutional arrangement, particularly at local levels; should use the existing institutional system for implementation of National Action Plan on forest protection and development;
Provincial REDD+ Steering Committee (PRSC) of 4/6 provinces are established with early support from GIZ and other partners

## Slide 19
National REDD+ Steering Committee
Vietnam REDD+ Office
Supporting Entities
Universities & research institutions
National REDD+ Network
Sub-Technical working groups
International supported projects/Progs.
Consulting agencies, independent experts
Provincial REDD+ Steering Committee
District and Commune REDD+ Taskforce
National policy-making level
Supervision, & Coordination
Forest managers and local communities/other stakeholders
Management at local levels
VNFOREST
NC on Climate Chang;
MARD & line Ministries
Implementing level

## Slide 20: Fruitful discussions on cooperation with other REDD+ initiatives/progs
  UN-REDD Phase II: technical building & demonstration REDD+ activities in 6 pilot provinces of which 3 provinces are located in proposed ER Prog.’s site;
  USAID: the Vietnam Forests and Delta Prog. And the Lowering Emissions from Asia Forests (LEAF)
  GIZ, Kfw, BMU: SFM & co-management of forests, reforestation &CO2 sequestration, technical capacity building, safeguards), SFE reform
  EU: Climate Smart Agriculture
  WB: supports for smallholder plantations in 3 provinces from 2012-2015, US$ 30 million; rehabilitation of mangrove forests

## Slide 21: 2.3 Continuation of development of interim REL/FRL
Historical NFI data for 5 time points: 1990, 1995, 2000, 2005 and 2010 was improved by using RS imagery and data screening with support from JICA and Finland;
Interim REL for the proposed option 1 is developed based on the improved NFI data (used the national databases);
However, the interim REL should be be refined by using improved data and methodology, and required technical and financial support;

## Slide 22: 2.4 Analysis of forest changes and key driving forces 1991-2010, measures

## Slide 23: 2.4 Analysis of forest changes and key driving forces 1991-2010, measures

## Slide 24: 2.5 Design the MRV Framework
Monitoring of
Forest resources,
REDD+ implementation
LMS
EF (NFI)
GHG-I
M
M(RV)
National Forest Monitoring System
National REDD+ Information System
Information on safeguards

## Slide 25: Continue to design the FMS
Work with FAO, BMU/SNV & RS data suppliers on improving the methods, parameters/indicators and producing demonstrations
  Agreed that parameters should be simple and practical, close linkages with result-based indicators
  Application of remote sensing imagery (high to very high-resolution) to make wall-to-wall forest/land use mapping
  Continue to test and develop detailed guidelines on Participatory monitoring
Completed the improved forest monitoring methods in Ha Tinh provinces which was invested by government budget

## Slide 26: Finalization of development of Emission Factor (EF) & Manuals
    Development of Destructive measurement for Allometric Equations for KEY natural forest types and major species for plantations); Report and database of AE is available at www.vietnam-redd.org/

## Slide 27: 2.6 Development of policies on transparent and effective data management
Data management and data sharing: completed pilot work in Thanh Hoa province and to develop National Forest Monitoring and Information System (FORMIS) - the project proposal is approved
Started to design a policy on development of registry system for mitigation projects

## Slide 28: 2.7 Designing mechanisms to address safeguards (1/2)
Recruited team of 2 international experts and 2 national specialist to:
Review current policies and instruments in comparison with Safeguards in the Cancun Agreement and WB regulations
Then, define the roadmap for addressing safeguards, and
Propose a sets of indicators, policies
Work with UN-REDD and FCPF to develop national manual for FPIC;
Organization of sub-technical working group meetings on Safeguards

## Slide 29: 2.7 Designing mechanisms to address safeguards (2/2)
Grievance Redress Mechanism (GRM): a) a complaint mechanism, b) Laws on Complains and Denouncement
Assurance of carbon rights and forestland tenure rights
Hired an legal specialist to review all government regulations on carbon rights to identify the gaps and actions
Reviewed status of forestland allocation and tenure in the proposed areas
Discussed with UN-REDD Phase II and USAID-funded VFD to provide support on improving forestland tenure rights

## Slide 30: 2.6 Development of information system on safeguards and its guidelines
Recruited team of 2 international experts and 2 national specialist to:
Review current policies and instruments in comparison with Safeguards in the Cancun Agreement and WB regulations
Then, define the roadmap for addressing safeguards, and
Propose a sets of indicators, policies
Work with UN-REDD and FCPF to develop manuals for FPIC;
Organization of sub-technical working group meetings on Safeguards
Grievance Redress Mechanism (GRM): a) a complaint mechanism, b) Laws on Complains and Denouncement

## Slide 31: 2.7 Designing BDS
National REDD+ Fund is proposed to be designed for managing and distributing revenue from REDD+ regardless from FCPF ER, UN-REDD or other Progs/Projects
Payment for REDD+ should be incorporated with payment for PES and other inventive progs to ensure that the payment will be based on ER performance to ensure transparency and equity, and avoid double payments;
Organized two national consultation workshops on designing BDS;
The proposal on establishment of National REDD+ Fund is submitted to MARD;

## Slide 32: Next Steps
Plan for submission of ER-PIN: Sept. for CF meeting in October 2013
Plan for March – June:
Finalization of selection of ER Prog scale of location
Selection of activities under the ER Prog
Continue to address safeguards requirements
Continue to develop FMS options and estimate expected emission reductions under the ER Prog
Continue the stakeholder consultations on above activities; consultation for full ER-PIN will be done from late July 2013
Continue to work with other international partners to cooperate in the ER prog site

## Slide 33: Relationship between Readiness grant and ER program
What is relationship between the FCPF Readiness Grant, UN-REDD and other REDD+ projects, and the ER Progs?
To provide support for National REDD+ Action Program (NRAP), particularly the REDD+ readiness preparation (R-package)
To support for providing inputs for development of ER-PIN
To provide support for implementation of policies, activities that contribute obtain objectives of ER Program

## Slide 34
Thank you very much for kind attention!